## PRP
Peshawar Revitalization Plan (PRP) 2026-27 High Impact Projects
S.No. | Area | Sector | Scheme Code | Scheme Name | Scheme Status | Scheme Type | Cost | Releases 2025-26 | Actual Exp: 2025-26 | Allocation (Local) 2026-27 | Remarks
1 | KP | Urban Development | 251597 | Construction of Northern Section of Ring Road (Missing Link) from Warsak Road to Nasir Bagh Road (Km 5+000 to Km 13+700) (Phase-II) (PRP). PDWP 25-02-2026 | A | G | 9673.24 | 6000 | 1000 | 2000 | Contract for Warsak and Palosai flyover Awarded, work commenced, completion deadline is December 2026
2 | KP | Urban Development | 251611 | Uplifting of Existing 34 No. Parks (PRP) PDWP 25-02-2026 | A | G | 999.691 | 581 | 0 | 418.691 | Work Commenced, Completion Deadline is January 2027.
3 | KP | Urban Development | 251612 | Installation/Rehabilitation of Electric Poles/Lights, Cabling etc. on Ring Road and GT/Jamrud Road (PRP). PDWP 25-02-2026 | A | G | 569.226 | 569 | 0 | 0.226 | 2nd time tendered, Technical Bid Evaluation held, financial bids to opened on 23/07/2026. Completion Deadline set for February 2027.
4 | KP | Urban Development | 251640 | Upgrading and Uplifting Major Arterial Roads/Routes of Peshawar City, Phase-I (PRP). PDWP 13-05-2026 | A | G | 3417.28 | 0 | 0 | 3417.28 | Technical Bids opened on 20/07/2026. Evaluation in progress.
5 | KP | Urban Development | 251641 | Upgrading and Uplifting Major Arterial Roads/Routes of Peshawar City, Phase-II (PRP). PDWP 13-05-2026 | A | G | 4588.48 | 4492 | 0 | 96.48 | Technical Bids opened on 09/07/2026. Evaluation in progress.
6 | KP | Urban Development | 251642 | Construction of Level-2 Flyover at Ring Road-GT Road Intersection, Peshawar Revitalization Plan (PRP). PDWP 13-05-2026 | A | G | 6960.37 | 0 | 0 | 6960.37 | NIT Published, Technical bids to be opened on 28/07/2026
7 | KP | Urban Development | 261258 | Upgrading and Uplifting Major Arterial Roads/Routes of Peshawar City, Phase-III (PRP). | B | N | 5600 | 0 | 0 | 3000 | Field surveys in Progress. PC-I to be submitted up to 30/09/2026
8 | KP | Urban Development | 261259 | Upgrading and Uplifting Major Arterial Roads/Routes of Peshawar City, Phase-IV (PRP). | B | N | 5200 | 0 | 0 | 3000 | Field surveys in Progress. PC-I to be submitted up to 31/10/2026
9 | KP | Urban Development | 260564 | Undergrounding PESCO Supply cabling (Pir Zakuri to Karkhano) (PRP) | B | N | 5240 | 0 | 0 | 1000 | NESPAK Engaged for Design and preparation of PC-I. PC-I to be submitted up to 31/10/2026
10 | KP | Urban Development | 260565 | Construction of Link Road from Hayatabad Industrial Estate to Northern Bypass, Peshawar (PRP) | B | N | 3500 | 0 | 0 | 100 | As No Feasible option to directly connect Industrial estate to Northern bypass Road is available, it was decided to opt alternative link road to connecting industrial estate via GT Jamrud Road with Ring road and Nothern Bypass junction at the eastern side of karkhano Markets. Land and Construction PC-I of the project has been framed and will be submitted to LGE&RDD up to 24/07/2026
11 | KP | Urban Development | 260566 | Construction of Ring Road Missing Link (Nasir Bagh to RMT) (Phase-III) (PRP) | B | N | 9462 | 0 | 0 | 1500 | Pc1 prepared submitted by consultant for review will be submitted to P&D next week
12 | KP | Urban Development | 260567 | Construction of under Passes on University Road, Ramdas-Chungi and Lahori Chowk (PRP) | B | N | 14000 | 0 | 0 | 3799.948 | Design for Ramdas chungi flyover is completed, PC-I for phase-I will be submitted 31/07/2026 and PC-I for Phase-II (University Road) will be submitted upto
13 | KP | Urban Development | 260568 | Development of Theme Park (PRP) | B | N | 2314 | 0 | 0 | 1000 | M/S NESPAK has been engaged on G to G basis and has commenced their services. The consultant has been tasked to complete their assignement within 3 months period i.e. by 02/10/2026
14 | KP | Urban Development | 260569 | Development of Hi-tech Children Park (PRP) | B | N | 750 | 0 | 0 | 750 | M/S NESPAK has been engaged on G to G basis and has commenced their services. The consultant has been tasked to complete their assignement within 3 months period i.e. by 02/10/2026
15 | KP | Urban Development | 260616 | Establishment of four Slaughter houses in Peshawar (PRP). | B | N | 1000 | 0 | 0 | 150 | Unapproved.
16 | KP | Urban Development | 260672 | Feasibility Study & Establishment of Fruit & Vegetable Markets in Peshawar (PRP). | B | N | 2500 | 0 | 0 | 1000 | Unapproved.
17 | KP | Urban Development | 250115 | Construction of Underpasses at Various Traffic Hotspots on Ring Road, Peshawar (PRP). PDWP 16-02-2026 | A | G | 9756.694 | 5000 | 0 | 4756.694 | Contract Awarded.
18 | KP | Urban Development | 251607 | Hiring of Consultancy services for Feasibility Studies, Detailed Engineering Design of “Frame of Peshawar” at entry from GT Road/M-1 and Designing of Entry Gates at Charsadda Road and Kohat Road, Peshawar (PRP). PDWP 16-02-2026 | A | G | 16.614 | 0 | 0 | 16.614 | NESPAK Engaged .
19 | KP | Urban Development | 251615 | Feasibility Studies, Uplifting, Conservation and Revitalization of the Walled City Peshawar (PRP). PDWP 25-02-2026 | A | G | 30 | 0 | 0 | 30 | F/S under process
20 | KP | Urban Development | 251614 | Supply/Erection of Street Light Accessories/New Installation at various NC’s of Directorate of Eastern Zone CMG Peshawar (PRP). PDWP 25-02-2026 | A | G | 300 | 299.999 | 0 | 0.001 | Procurement stage
21 | KP | Urban Development | 251613 | Purchase of Funeral Including Fabrication/Modification of Chassis for Directorate of Eastern Zone CMG Peshawar. PDWP 25-02-2026 | A | G | 175 | 174.999 | 174.999 | 0.001 | Procurement stage
22 | KP | Urban Development | 251297 | Improvement of Water Supply Distribution Network in Peshawar (PRP). PDWP 15-01-2026 | A | G | 1140.247 | 49 | 0 | 300 | Works Commenced.
23 | KP | Drinking Water & Sanitation | 251627 | Water Supply Schemes in PHE Division Peshawar-I & Peshawar-II (PRP). | A | G | 4245.367 | 300 | 300 | 2000 | Works Commenced.
Total | [6 empty] | 91438.209 | 17465.998 | 1474.999 | 35296.305
|  | Total PRP Schemes | 23
|  | Approved Schemes | 13
|  | Unapproved Schemes | 10